## Open Questions
# | Category | Priority | Status | Question / Item | Why it matters | What I need from you | How to reply
1 | Pricing regression | BLOCKING | Open | Anonymized approved historical proposals for the pricing regression suite | Milestone 7 (pricing) cannot be marked complete until historical totals are reproduced or each discrepancy is documented | 2-5 anonymized approved proposals as fixtures (format in tests/regression/README.md) | Attach the files; synthetic IDs, no PII
2 | monday.com integration | HIGH | Open | Real monday deal-board column IDs | mapping.ts currently uses placeholder column ids (status, numbers, ...); sync will target the wrong columns until corrected | The column IDs for stage, funding status, budget, organization on your deal board | List each field = column id in chat
3 | Deployment | HIGH | Open | Vercel + Postgres environment secrets | App will not boot in production without validated env; secrets must never be in source | Confirm DATABASE_URL (pooled), DIRECT_URL (direct), MONDAY_API_TOKEN, MONDAY_SIGNING_SECRET, MONDAY_DEALS_BOARD_ID are set in Vercel | Confirm done, or ask for help setting them
4 | Environment / testing | RECURRING | Open | Run all checks and tests on a real machine | I cannot execute code here, so no milestone has real test results yet | Run: pnpm db:migrate && pnpm check && pnpm test | Paste output if you want me to fix failures
5 | Project context | MEDIUM | Open | The approved architecture / implementation roadmap document | I built on reasonable assumptions; the doc lets me reconcile decisions | The doc, if it exists | Attach it
6 | Proposal / PDF | LOW | Open | Confirm PDF pagination on each proposal template | Page breaks should look right when exported | A Save-as-PDF pass on each template | No reply needed unless something looks off
7 | Branding | MEDIUM | Open | Logo placement in proposals | You said you want the Summit logo in the proposal | Where it should appear (cover only, or cover + running header) and desired size | Reply in chat; logo file already uploaded
8 | Foundation stack | — | Resolved | Framework / ORM / DB / auth / test stack / package manager / staging | Needed to scaffold Milestone 1 | You chose "make it simple" | Resolved: Node22+pnpm, Fastify, Prisma+Postgres, JWT+argon2, Vitest+Playwright, GitHub Actions, Docker/Render
9 | monday.com integration | — | Resolved | Sync direction / entities / trigger / auth | Defines the integration milestone | You answered: two-way, deal tracking, webhooks, token+secret env | Resolved
10 | Deployment | — | Resolved | Hosting targets | Determines deploy config | You confirmed GitHub + Vercel | Resolved (Vercel config added)